## WRISM V1 Issues & Bugs
KDA Department of Water Resources - WRIS Mobile Application V1 Issues/Bugs/Enhancements
ID | Work Item Type | Bug Short Description/Name | Bug Details / Steps to Reproduce
| Bug | General--Date filters not working properly | In the review tab, I tried to filter by date modified, so I selected "Is equal to" and used the calendar to select 6/19/15. The list of forms changed and none were showing. There were two sync times that were dated 6/19/15 that should have shown up.
| Issue | CCA Form--Info Tab--Overlap File No--Field not populating | Overlapping file number not showing. File No. 22230-00 (Pdiv 84260) should has an overlap with File No. 35181 (also Pdiv 84260) | All items listed in this table were noted by the KDA WRISM testing team as issues, bugs or enhancements during the first round of WRISM user acceptance testing. Each of these items have been addressed or added to the second version of the WRISM application that is currently in user acceptance testing.
| Bug | CCA Form--Info Tab--Chg No C--Field not populating | Change number not populating. File No. 22230-00 (Pdiv 84260) should have a C1 and a C2
| Bug | CCA Form--Info Tab--Water Correspondent--Field pulling wrong/no info | For example, File No. 40966 (Pdiv 70061) shows Edna M Doperalski as the correspondent, but she was the applicant and is no longer part of the file. There are other files doing this and some files are not pulling any information.
| Issue | CCA Form--Info Tab--Field length | Compliance comments needs expanded. It is only 30 characters right now. Around 500 characters would be nice.
| Issue | CCA Form--Info Tab--Field length | Water Current Use field not long enough.
| Bug | CCA Form--Info Tab--If PD chg, Old PD ID--Field not working | If a number is put in and saved, it will not show up in the field when the form is opened at a later time.
| Issue | CCA Form--Points of Div Tab--GPS format | We use decimal degrees
| Issue | CCA Form--Points of Div Tab--Actual Point of Diversion History | When I click the arrow, a window pops up saying "Drag a column header and drop it here to group by that column." What is supposed to show up here?
| Issue | CCA Form--Points of Div Tab--Actual/Authorized Point of Diversion | The box after these headings are just one long text. In WRIS, there are four separate fields for the quarter descriptions and three separate boxes for the lot. The authorized should be populating from WRIS?
| Issue | CCA Form--Equipment--Power Unit Tab--Fuel drop-down | Add Natural Gas and Propane to the list
| Issue | CCA Form--Equipment (Cont)--Well Info Tab--missing units | The Original Depth, Static Water Level When Drilled and Depth to Water Below LSD all need units (feet)
| Issue | CCA Form--Equipment (Cont)--Meter Information Tab--Suggestion | There are times when one Pdiv will have more than one meter. Can this be accommodated by the form?
| Issue | CCA Form--Equipment (Cont)--Meter Information Tab--format change | "In Compliance" check box should be renamed "Installed Properly?"
| Issue | CCA Form--Equipment (Cont)--Meter Information Tab--rounding | when entering Size (ID), Size (OD) and Measured Size (OD) the form allows the user to enter an adequate number of digits, but when saved, it rounds to only two decimals when three are needed.
| Issue | CCA Form--Equipment (Cont)--Meter Information Tab--rounding | Meter Reading only shows two decimals. This needs to show at least four decimals. May actually be better as a text box so that the number of decimals can be customized, from zero up to four.
| Issue | CCA Form--Equipment (Cont)--Meter Information Tab--Timed Flow Rate Tab--rounding | The Beginning Reading and Ending Reading fields need to show at least four decimal places.
| Issue | CCA Form--Equipment (Cont)--Meter Information Tab--Timed Flow Rate Tab--Time field rounding | The time field does not have a unit and is rounding to a whole number. Clarification is needed and potentially some decimals.
| Issue | CCA Form--Water Use tab | No place for current meter reading
| Issue | CCA Form--Water Use tab | Fields are rounding to the nearest 1. Actually need at least three decimal places with no rounding
| Issue | CCA Form--Water Use tab | Can the Authorized Quantity and Rate be pulled automatically from WRIS?
| Issue | CCA Form/FIR Form--Water Use tab | Some of this information is in WRIS. Can some of it be pulled automatically, at least for the most recent year?
| Bug | FIR Form--Info Tab--Landowner and Water Correspondent field | The fields do not always populate, and the Water Correspondent field appears to pull the wrong contact when it does populate.
| Issue | FIR Form--Points of Div tab--fields not auto filling, or fillable | Approved Quantity, Approved Storage Quantity and Approved Storage Rate not fillable. These and Approved Diversion Rate could all pull from WRIS
| Issue | FIR Form--Points of Div Tab--GPS format | We use decimal degrees
| Issue | FIR Form--Points of Div Tab--Actual Point of Diversion History | When I click the arrow, a window pops up saying "Drag a column header and drop it here to group by that column." What is supposed to show up here?
| Issue | FIR Form--Equipment--Power Unit Tab--Fuel drop-down | Add Natural Gas and Propane to the list
| Bug | FIR Form--Equipment (cont) tab--Well Information--not pulling enough Pdivs | I am completing the FIR form for Pdiv 81720, which is the geocenter for a battery of four wells. I went to fill in the well info for each Pdiv, but it only gave me the Pdiv for 81721 and not the other three. This was the same in the pump, gearhead and power unit sections.
| Issue | FIR Form--Equipment (Cont)--Well Info Tab--missing units | The Original Depth, Static Water Level When Drilled and Depth to Water Below LSD all need units (feet)
| Issue | FIR Form--Additional Tab-- Additional Requirements Tab--Suggestion | There are times when one Pdiv will have more than one meter. Can this be accommodated by the form?
| Issue | FIR Form--Diversion Rate Tab--Non-Intrusive Meter Test--time fields | This field needs at least two decimal places to be accurate
| Issue | FIR Form--Diversion Rate Tab--Non-Intrusive Meter Test--measured wall field | needs three decimals
| Issue | FIR Form--Diversion Rate Tab--Non-Intrusive Meter Test--ending / beginning meter reading fields | unit is always gallons and they need three decimal places
| Issue | FIR Form--Diversion Rate Tab--Installed Meter Test--time fields | The time field does not have a unit and is rounding to a whole number. Clarification is needed and potentially some decimals.
| Issue | FIR Form--Diversion Rate Tab--Non-Intrusive Meter Test--time fields | The time field does not have a unit and is rounding to a whole number. Clarification is needed and potentially some decimals.
| Issue | Map Part--Differentiating GPS icon from P/Ds | If the blue of the GPS icon cannot change, change the P/D color scheme
| Issue | Map Part--formatting | Remove gray grid in background
| Issue | Map Part--Section Lines | make more prominent, say make them red?
| Issue | Map Part--Legals | Can the sections have a label? Can they be made a separate base layer?
| Issue | Map Part--Aerial Images | Aerial images need to show up sooner when zooming in.
| Bug | Map Part--Using pen | The stylus pen will not pan the map view
| Bug | Map Part--Side loading trouble | Side loading a polygon shapefile crashes the program
| Bug | Map Part--Side loading files--attributes | Had difficulty identifying a side loaded p/d shapefile. Can the attributes be identified through the identify tool?
| Bug | Map Part--Some P/Ds not showing up right | File No. 21431 (Pdiv 34677) is plotting wrong, but the GPS is correct in WRIS. The P/D is plotting right in ArcMap, which is pulling from WIMAS.
| Bug | GPS--General | Occassionally, the Stockton Tablet will not locate using the GPS. If the program is restarted while outside, it will work.
| Bug | Search--GPS issue | One tablet (GCFO) would move/relocate the searched point of diversion when the tablet screen was touched
| Issue | Pre-Planning Tool--Missing functionality? | File No. 43288 has 14 lines. There are only five P/Ds authorized by the water right. One set should be New App, one set should be a change and one set should be a FIR for actions. The action type could not be changed, as all said new appliction for the Action Type / Reason. I assigned P/Ds to five of the entries, so there are now nine left.
| Bug | Camera--Crash in portrait view | One tablet (GCFO) will crash the program if the tablet is rotated to portrait view. In Stafford, trying to use the camera crashes the program at any time.
| Issue | Camera--Resolution | Is the image resolution set by the application or by the Panasonic dashboard?
| Issue | Identify Tool--Difficult to use | If a p/d is not hit just right, the identify action will cancel itself out. Can there be a larger tap area around a P/D? Can the identify tool be on or off.
|  | Water Measure Tool--add units | units are feet
|  | Photo resolution | The minimum was decided to be 1024 x 700. The field offices would prefer a resolution of 1600 x 1200.
|  | Maps: Scale for aerial images to appear | It was requested the aerials show up at 1:48,000
|  | CCA & FIR Form: Equipment (cont.) Tab: Meter Information: Distance Upstream/Downstream | Could the words "from sensor" be added?
| Issue | General--Counting field activities | Is there a way to query the number of visits during a specific time period as well as the inspector for reporting purposes? For example, can we see how many field inspections Elizabeth did during a specific 2 week period?
| Issue | General--option to delete an action | There needs to be an option to delete an action, whether in the review screen or at the P/D level.
| Issue | CCA Form/FIR Form--all check boxes | It was suggested to possibly use Y/N boxes instead of check boxes. That way the field user knows that all fields have been addressed. With check boxes, one may get back to the office and wonder if they missed a section or if they were all really supposed to be not checked.
| Issue | CCA Form/FIR Form--saving | Can the forms be designed to auto save or prompt to save? During a field test, data was lost because the save button was not hit. If a form is begun on accident, it can be deleted.
| Issue | CCA/FIR Forms--shift to history | As soon as a form is opened and then closed, the action immediately shifts to history, even if no data was saved. Is there a way to prevent this?
| Issue | Action Item--additions | There is a need to rename/add reasons for visits.
| Issue | CCA Form--Info Tab--Fields in odd spot | For familiarity, the last four check boxes should be on the Equipment (cont.) tab under a heading called Additional Conditions, or a that could be a tab all its own.
| Issue | CCA Form--Points of Div Tab--Add Leobase | Would like the application to auto-calculate distances from the southeast corner of section using LeoBase 7 database
| Issue | CCA Form--Equipment (Cont)--Well Info Tab--missing field | Please add a field for the MP height. This wasn't on the original form and was usually added.
| Issue | CCA Form--Equipment (Cont)--Meter Information Tab--Add field | Add meter location drop down box. Options: well, pivot, other/see comments
| Issue | CCA Form--Equipment (Cont)--Meter Information Tab--format change | Manufacturer, Type, Units, and Multiplier Factor could be changed to dropdown menus. There are limited options here.
| Issue | CCA Form--Equipment (Cont)--Meter Information Tab--delete field | Compliance date field is unnecessary. The date of the visit is the compliance date and this can be found on the Info tab.
| Issue | CCA Form--Equipment (Cont)--Meter Information Tab--format change | Distance Upstream, Downstream, Reading, Pressure Gauge, GPM, Instant Rate, Non-Intrusive Rate and Other should all be moved above the Characteristics Tab to improve flow and readability when filling out in the field.
| Issue | CCA Form--Equipment (Cont)--Meter Information Tab--Seal Information Tab--extra field | Remove Manufacturer Seal field. This is repetitive since it is already documented in the Security Seal Stamp Labeled field just above it
| Issue | CCA Form--Equipment (Cont)--Meter Information Tab--Timed Flow Rate Tab--suggested stopwatch addition | A request was made for a stop watch function that would automatically populate the Time field
| Issue | CCA Form--Equipment (Cont)--Meter Information Tab--Timed Flow Rate Tab--suggested calculation addition | This Tab can use the same built in calculations as are used in the FIR form on the Meter Test Tabs
| Issue | FIR Form--Info Tab--extra heading | File No(s). Is not populating anything and can probably be removed. The overlaps are described elsewhere.
| Issue | FIR Form--Info Tab--In Compliance / Date heading--format | The Investigation? Check box should probably be renamed Compliance Investigation?
| Issue | FIR Form--Points of Div Tab--Add Leobase | Would like the application to auto-calculate distances from the southeast corner of section using LeoBase 7 database
| Issue | FIR Form--Points of Div Tab--Actual/Authorized Point of Diversion | The box after these headings are just one long text. In WRIS, there are four separate fields for the quarter descriptions and three separate boxes for the lot. The authorized should be populating from WRIS?
| Issue | FIR Form--Equipment (Cont)--Well Info Tab--missing field | Please add a field for the MP height. This wasn't on the original form and was usually added.
| Issue | FIR Form--Additional Tab-- Additional Requirements Tab--Rename tab | This could be called Meter, then Meter Requirements. Additonal Equipment is probably ok.
| Issue | FIR Form--Additional Tab-- Additional Requirements Tab--Add field | Add meter location drop down box. Options: well, pivot, other/see comments
| Issue | FIR Form--Additional Tab-- Additional Requirements Tab--field format change | Manufacturer, Type, Units, and Multiplier Factor could be changed to dropdown menus. There are limited options here.
| Issue | FIR Form--Diversion Rate Tab--Non-Intrusive Meter Test--ending / beginning meter reading fields | unit can be acre-feet, acre-inches and gallons. The field needs three decimal places and the equation will be different depending on the unit. The calculation appears to be designed for gallons.
| Bug | FIR Form--Diversion Rate Tab--Non-Intrusive Meter Test--%error field | Field did not populate on Pdiv 81721 under FIR for PDIV 81720. Maybe because the second rate is way off. Also, each test needs its own %error calculation
| Issue | FIR Form--Water Use Tab--fields in wrong spot | Everything after Crops irrigated should be on a separate area, not each water use year. The fields at the bottom of the tab are not fillable and are not appearing to populate.
| Issue | FIR Form--Water Use Tab--Water Used field unit | The unit will not always be gallons. It would be best to have a separate dop down box for the unit.
| Issue | Map Part--Default view when opening | Help set up each field office with changing the default open view to an area local to their field office. For example, the Stafford laptop zooms to the area, but the Stafford tablet zooms to the Garden City area.
| Issue | Map Part--P/D shapefile--definition query | show only active P/Ds. Is there a way to make the Action Required P/Ds always show on top?
| Issue | Map Part--P/D shapefile--definition query part 2 | Several have asked if it is possible to have the ability to turn the no action needed P/Ds on and off while keeping the action needed P/Ds
| Issue | Map Part--P/D shapefile--formatting | More detailed symbology is needed for the P/Ds. The level of detail would include reason for visit and also to add a third color for level of action (first visit vs second visit needed for not in compliance)
| Issue | Map Part--P/D shapefile--labeling | Change P/D label from Pdiv to File No.
| Issue | Map Part--Scale | Can a scale reference be added to the map view?
| Issue | Map Part--Measurement tool | Can a measure tool be added, on that does both lines and polygons?
| Issue | Map Part--Navigation tools | Currently with the handheld GPS, one can search by either the well name or by nearest point. Once a point has been chosen, one can then navigate to that location. It is nice to see the line from the current location to the next site visit as well as the distance to that point (i.e. 1.5 miles or 15 miles). Can see the available roads.
| Issue | Map Part--Side loading files--Symbology | P/D defaults to black, needs to be a different color, preferably a different shape.
| Issue | GPS--General | Need to be able to take GPS coordinates that do not modify a P/D location. For example, taking a GPS of the old well, an unauthorized well, or a pivot point. There would need to be an associated comment box.
| Issue | GPS--General | Would like to use multiple GPS locations and LeoBase7 database to calculate distance between two points.
| Issue | GPS--General | Would like the well selected/searched to be indicated in some fashion, say highlight in a bright blue like ArcMap does.
| Issue | Search--more search options | need to be abe to search by File No
| Issue | Review Tool--Extra step needed? | Can a check box be added that designates a form that is ready for review. If one goes out and does a check, they don’t want the QA/QC to occur until after the form has been cleaned up in the office.
| Issue | Review Tool--Notification | Can a notification be sent via email that a review is ready? Or will this need to be an internal workflow adjustment?
| Issue | Review Tool--additional fields for filtering | Add Field office and county as options
| Issue | Pre-Planning Tool--Add fields for filtering | Add Field office, File No. and County as options
| Issue | Pre-Planning Tool--excessive taps | It takes three taps to assign the P/D to the action: One to hightlight the line, one to activate the drop box and one to open the drop box. Is there a way to cut down on this?
| Issue | Add Tool--Place of Use--Add circle | The option to draw a circle as well as a polygon would be very useful
| Issue | Add Tool--Place of Use--determine area | It would be nice to have the area show up in acres in the description box.
| Issue | Water Measure Tool--add field | Add an MP Height field. For the well network, the mp height can be pulled from the database.
|  | Water Measure Tool--add calculations | DBLS can be calculated as Hold - Cut - MP Height = DBLS
|  | Water Measure Tool--enhancements | This part needs tied to our water level database for a network separate from WRIS
|  | GMD access | The GMDs currently have issues with using the application due to access to DWR networks. I'm sure this is being discussed, but I just wanted to get it in writing.
|  | General Formatting | In the forms, is it possible to bold the field description to differentiate it from the field information? For example, on the info page, Bold Field Office No., but leave the field value normal.
|  | General Formatting | Could the form fields be grayed or given a shading of some sort like the drop down boxes? This would help visually to see what needs completed.
|  | CCA Form: Equipment (cont.) Tab: Meter Information: Active designation | Over time, meters are replaced and occassionally, water users have multiple meters, but only certain ones are reported. Is there a way to add an "active" check box that would designate the currently used meter? More information can be provided for clarification.
|  | CCA & FIR Form: Equipment (cont.) Tab: Meter Information: Distance Upstream/Downstream | Could a draw form be inserted in this part of the form so that a sketch of the meter installation could be completed? The sketch could be converted to an image to be inserted in our report.
| Issue | CCA/FIR Form--Fields Missing | hour meter present (Y/A), hour meter location, hour meter reading, DWR seal required (Y/N), Anti-Reverse gears required (Y/N), Anti-Reverse gears present (Y/N) are fields that are not found on CCA form and need to be added. Location can be discussed.
| Issue | FIR Form--Lands tab--fields are not proper type | The Lands to be included on Certificate and Lands irrigated are not usable as designed. They need to be a fillable table for irrigation. The comment box is good for non-irrigation water rights.